## Jobs
Job ID | Category | Job Description | Location | Maintenance Type | Status | Estimated Completion | Next Job Date
ACMV-001 | ACMV | AHU filter replacement | Level 3 Plant Room | Preventive | In Progress | Week 1 January 2026 | Week 1 April 2026
ACMV-002 | ACMV | Chiller quarterly servicing | Basement 1 Chiller Plant | Preventive | Yet to Start | Week 2 January 2026 | Week 2 April 2026
ACMV-003 | ACMV | FCU water leak rectification | Level 7 Office | Corrective | Completed | Week 4 December 2025 | -
ACMV-004 | ACMV | Cooling tower chemical dosing | Roof Level | Preventive | In Progress | Week 3 January 2026 | Week 3 February 2026
LFT-001 | Lift & Escalator | Passenger lift No.1 monthly service | Tower A Lobby | Preventive | Completed | Week 1 January 2026 | Week 1 February 2026
LFT-002 | Lift & Escalator | Escalator step chain adjustment | Level 1 to Level 2 | Corrective | In Progress | Week 2 January 2026 | -
LFT-003 | Lift & Escalator | Annual load test — service lift | Tower B Service Core | Preventive | Yet to Start | Week 4 February 2026 | Week 4 February 2027
ELE-001 | Electrical | LV switchboard thermal scanning | Main Electrical Room | Preventive | Yet to Start | Week 3 January 2026 | Week 3 July 2026
ELE-002 | Electrical | Emergency lighting battery test | All Staircases | Preventive | In Progress | Week 2 January 2026 | Week 2 April 2026
ELE-003 | Electrical | Faulty ballast replacement | Level 5 Corridor | Corrective | Completed | Week 1 January 2026 | -
ELE-004 | Electrical | Generator load bank test | Genset Room | Preventive | Yet to Start | Week 1 March 2026 | Week 1 September 2026
FIR-001 | Fire Protection | Sprinkler head inspection | Level 1 to Level 10 | Preventive | In Progress | Week 2 January 2026 | Week 2 July 2026
FIR-002 | Fire Protection | Fire alarm panel functional test | Fire Command Centre | Preventive | Completed | Week 1 January 2026 | Week 1 February 2026
FIR-003 | Fire Protection | Hose reel pressure rectification | Level 4 Riser | Corrective | Yet to Start | Week 3 January 2026 | -
FIR-004 | Fire Protection | Fire pump weekly churn test | Pump Room B1 | Preventive | In Progress | Week 2 January 2026 | Week 3 January 2026
PLB-001 | Plumbing & Sanitary | Water tank cleaning and disinfection | Roof Tank Room | Preventive | Yet to Start | Week 4 January 2026 | Week 4 July 2026
PLB-002 | Plumbing & Sanitary | Blocked floor trap clearing | Level 2 Male Toilet | Corrective | Completed | Week 1 January 2026 | -
PLB-003 | Plumbing & Sanitary | Booster pump servicing | Basement Pump Room | Preventive | In Progress | Week 3 January 2026 | Week 3 April 2026

## Guide
HOW TO UPDATE THIS WORKBOOK
This file is read by the Facilities Management Telegram bot.
Edit it in Excel Online. OneDrive syncs your changes automatically and the bot
picks them up within seconds — no restart is needed.
RULES
1. Only edit the 'Jobs' sheet. Do not rename it or any column header.
2. Category, Maintenance Type and Status all use dropdowns — always use them.
3. Enter dates as text in this exact style: Week 1 January 2026
(A real Excel date also works — the bot converts it to the same style.)
4. Put '-' in Next Job Date for one-off corrective jobs that will not repeat.
5. Add new jobs on the next empty row. Never leave a blank row in the middle.
6. To retire a job, delete its row. Do not blank out only some of the cells.
STATUS MEANINGS
Yet to Start — scheduled but no work has begun
In Progress — work has started, not yet handed over
Completed — work finished and verified
The sample rows currently in the Jobs sheet are examples. Delete them once
your real job records are entered.